## READ ME
Purpose | Capture acceptance criteria in support of testing SAPRO requirements have been met. These acceptance criteria will be aligned to the User Stories in the RTVM. The "Test No." from this spreadsheet will be inserted into the RTVM.
Graphic to the right --> export guidance
File POC | Dawn Riddle
Desiree
History / Log | createdfrom JIRA 28 Jan 2026. Update Tickets / new export from JIRA at end of each Sprint.

## SAPRO US and Detailed AccCrit
Last Update: 28 Jan 2026
Test No. | Issue Type | Parent summary | Issue id | Summary | Parent | Parent key | Custom field (Linked items) | Custom field (Workflow) | Description | Custom field (Acceptance Criteria) | Custom field (Acceptance Criteria) | Custom field (Stakeholders) | Status
CredMgmt_05 | Story | Initiate Application | 11525722 | As a [Learner], I want to access the latest D-SAACP Application for a renewal application. | 11523894 | ERM-2865 |  |  | If I am a first time applicant we want to make sure learners DO NOT fill out the *DD 2950 form.* This has created a lot of issues/need to redo things. The SARW-MS user interface should present the applicant with the current, correct version of the application form as indicated by persistent tags in the application footer. These tags will include info on: (Data source = Portal Backend) * Name of form (e.g, DD Form 2950 or DD Form 2950-1) * Form Version (e.g., FEB 2025) * Date of Update (e.g., Updated 02/05/2025) (if available) * Governing Policy (e.g., ‘Prescribed by DoDD 6495.03, DoDI 6495.03, and DTM 14-001’) Additionally, the application will be coded as fields in the UI. Applicants will be presented with the inital or refresher application questions/requirements appropriate to need. For renewal the learner will select the type of application they are submitting (New Application or Renewal Application) and will select which position they are seeking certification for the following. # SAPR Program Administrator. # SAPR VA. # Principal SARC. # Supervisory SARC. # Collateral Duty SARC # Special Assignment SARC # Collateral Duty SAPR VA # Special Assignment SAPR VA Note: Here is the criteria that will indicate if the field should be greyed out or not. !image-20251212-152453.png¦width=538,alt="image-20251212-152453.png"! MVP = coding the application versions into the UI. FOC = consider a configurable UI based on form upload. [NOTE: this will include mapping all data fields to DLE fields / stnds] ---- IMPLEMENTATION: All users will be presented an initial question that help determine whether or not they need to fill out a new or a renewal application. The question will ask them what type of application they are submitting. If they select new application, then they will be presented with a field to “Please upload your certificate from your completed D-SAACP pre-approved training courses” and a question to determine “which position are you seeking certification for”. If they select renewal application, they do not need to upload the D-SAACP training course certificate and will also be presented a question to determine “which position are you seeking certification for.” ---- MVP: hard coding and think about how we’re going to handle version changes going forward. | Feature: Access latest D-SAACP Application for renewal As a Learner, I want to access the latest D-SAACP Application So that I can complete my renewal application process. Scenario: Learner accesses the latest D-SAACP Application for a RENEWAL application Given: the Learner is logged into the system When: the Learner navigates to the My application section Then: the system should display a question asking what Application (new/renewal) they are submitting Then: the system should provide the latest version of the D-SAACP *Renewal* Application And the application should be clearly labeled as the latest and correct version with the following fields: - Name of form (e.g, DD Form 2950 or DD Form 2950-1) - Form Version (e.g., FEB 2025) - Date of Update (e.g., Updated 02/05/2025) - Governing Policy (e.g., ‘Prescribed by DoDD 6495.03, DoDI 6495.03, and DTM 14-001’) |  | SAPRO | In Progress
CredMgmt_06 | Story | Monitor Application Intake and Validation | 11525757 | As a [Learner], I want to be able to be notified of any problems with my application so that I can fix it | 11523898 | ERM-2867 |  |  | supervisors will comment on page as a whole OR on specific field(s) [feasibility for MVP?] and mark as needing applicant to change or not… templated comments or open comment fields? applicants are currently sent canned messages. Perhaps this is email notification that they need to contact XX. | Scenario: Applicant has submitted an application Given: an error exists in an application When: a reviewer makes a comment on the application Then: a templated email is sent to the applicant's email address AND / or an alert is sent to the applicant's UI. (according to applicant's set preferences) Reviewer enters comment on learner application which triggers comment box specific email message / UI alert. -Comment box 1 --> box specific email message / notification [approved message TBD] -Comment box 2 --> box specific email message / notification [approved message TBD] -Comment box 3 --> box specific email message / notification [approved message TBD] Learner receives canned email message email message states: <insert approved message> email contains link to comment section within application [is this MVP?] Notification alert appears on Learner UI. Alert indicates <insert approved message> |  | SAPRO | Backlog
CredMgmt_07 | Story | Initiate Application | 11525758 | As a [Learner], I want to access the latest D-SAACP Application for a new application. | 11523894 | ERM-2865 |  |  | If I am a first time applicant we want to make sure learners DO NOT fill out the *2950-1 form.* This has created a lot of issues/need to redo things. The SARW-MS user interface should present the applicant with the current, correct version of the application form as indicated by persistent tags in the application footer. These tags will include info on: * Name of form (e.g, DD Form 2950 or DD Form 2950-1) * Form Version (e.g., FEB 2025) * Date of Update (e.g., Updated 02/05/2025) * Governing Policy (e.g., ‘Prescribed by DoDD 6495.03, DoDI 6495.03, and DTM 14-001’) ---- * Additionally, the application will be coded as fields in the UI. Applicants will be presented with the inital or refresher application questions/requirements appropriate to need. For new, the learner will select the type of application they are submitting (New Application or Renewal Application) and will select which position they are seeking certification for the following. # SAPR Program Administrator. # SAPR VA. # Principal SARC. # Supervisory SARC. # Collateral Duty SARC # Special Assignment SARC # Collateral Duty SAPR VA # Special Assignment SAPR VA Note: Here is the criteria that will indicate if the field should be greyed out or not. !image-20251212-152453.png¦width=538,alt="image-20251212-152453.png"! # Additionally, they will have to ‘Please upload your certificate from your completed National Advocate Certification Program (NACP) pre-approved training course(s)’ ---- MVP = coding the application versions into the UI. FOC = consider a configurable UI based on form upload. [NOTE: this will include mapping all data fields to DLE fields / stnds] IMPLEMENTATION: All users will be presented an initial question that help determine whether or not they need to fill out a new or a renewal application. The question will ask them what type of application they are submitting. If they select new application, then they will be presented with a field to “Please upload your certificate from your completed D-SAACP pre-approved training courses” and a question to determine “which position are you seeking certification for”. If they select renewal application, they do not need to upload the D-SAACP training course certificate and will also be presented a question to determine “which position are you seeking certification for.” ---- MVP: hard coding and think about how we’re going to handle version changes going forward. | Feature: Access latest D-SAACP Application for new application As a Learner, I want to access the latest D-SAACP Application So that I can begin a new application process. Scenario: Learner accesses the latest D-SAACP Application for a NEW application Given the Learner is logged into the system When the Learner navigates to the My application section Then the system should display a question asking what Application (new/renewal) they are submitting when the learner selects new, the system displays 2 additional items: 1. upload of the D-SAACP certificate; 2. which position are you seeking cert for. Scenario: Learner accesses the latest D-SAACP Application for a NEW application Given the Learner is logged into the system When the Learner navigates to the My application section Then the system should display a question asking what Application (new/renewal) they are submitting when the learner selects renewal, the system displays 1 additional items: 1 which position are you seeking cert for. And the application should be clearly labeled as the latest and correct version with the following fields: - Name of form (e.g, DD Form 2950 or DD Form 2950-1) - Form Version (e.g., FEB 2025) - Date of Update (e.g., Updated 02/05/2025) - Governing Policy (e.g., ‘Prescribed by DoDD 6495.03, DoDI 6495.03, and DTM 14-001’) |  | SAPRO | In Progress
CredMgmt_08 | Story | Initiate Application | 11525759 | As a [Learner], I want my personal and organizational information pre-populated so that I don't have to re-enter data the system should already have | 11523894 | ERM-2865 |  |  | Pull from the ELRR to populate as many fields as possible. Identify from data model what specific fields will be pre-populated. All fields are required unless listed as optional. ---- ELRR Data fields: * Applicant First Name * Applicant Last Name * Applicant Middle Initial * Affiliation * Status * Rank * Grade Editable fields include: * Command * Installation * Work email address * DSN *_(optional data field)_* * Work telephone number * Phone Number ext. *_(optional data field)_* * SARC’s Email address *ELRR Supports all of these fields* ---- Data fields from HR System / ELRR: * 4.1.10.15 hasEmploymentRecord >> 4.1.8.10 Position * 4.1.10.15 hasEmploymentRecord >> 4.1.8.XX ApplicationId (Extension) * 4.1.3.4 LastName * 4.1.3.2 FirstName * Derive from 4.1.3.3 MiddleName OR 4.1.3.XX (Extension) - 4.1.3.57 HasMilitaryRecord - 4.1.10.1 militarybranch * 4.1.3.57 HasMilitaryRecord - 4.1.10.7 MilitaryCurrentStatus * 4.1.3.57 HasMilitaryRecord - 4.1.10.6 MilitaryCurrentRank * 4.1.3.57 HasMilitaryRecord - 4.1.10.31 CurrentPayGrade * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.1 OrganizationName * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.4 Facility or 4.1.7.5 Department * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.31 hasEmail * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.30 hasPhone * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.30 hasPhone ---- Design / Development Decision: We will move forward with fields we CAN gather from JWT, to get some data fields. The remainder of fields will be editable. As we connect to source HR systems, we can populate more fields and slowly move towards read only, where applicable. ---- Note on the below - need to determine validity of the data coming in via JWT with P1 on how we are receiving this information, most likely would recommend pulling from HR system and only CAC info from JWT. Data fields from JWT: "preferred_username": "jdoe", "given_name": "John", "activecac": "DOE.JOHN.1234567890" "name": "John Doe", "rank": "N/A" "email": ["john@company.com¦mailto:"john@company.com]" "affiliation": "Other", "organization": "Company, Inc", "group-full": [ "adl-ousd/sql-lrs/Impact Level 2 Authorized", "/Impact Level 4 Authorized", "/Impact Level 5 Authorized" ], !Image preview.png¦width=747,alt="Image preview.png"! ---- | Scenario: Learner (Applicant) is completing the DSACCP application and needs to provide personal info, job info, learning history, etc. Given: data is in the ELRR When: The applicant opens the application Then: the applicant's information will be pre-populated by the system. Given: the applicant's data is NOT in the ELRR When: The applicant opens the application Then: the applicant's information will NOT be pre-populated (fields will be empty) by the system and can be entered manually MVP: allow applicant to edit information instead of requesting edits to parent system. |  | SAPRO | To Do
CredMgmt_09 | Story | Initiate Application | 11525760 | As a [Learner], I want to see information for how to update pre-populated personal and organizational information so I can correct any errors | 11523894 | ERM-2865 |  |  | How does this info get back into the system? We talked about submitting a ticket? | Scenario: Learner (Applicant) is completing the DSACCP application and needs to provide personal info, job info, learning history, etc. Given: The applicant is viewing a page with pre-populated information When: The applicant hovers over a tool tip Then: the applicant will see information about where their info is being pulled from and if they can /how to edit it When: the applicant tries to edit a field (changing pre-populated field) Then: the applicant can change the information, saving it as data tied to the application (not to the system it pulled from to pre-populate) MVP: allow applicant to edit information instead of requesting edits to parent system. |  | SAPRO | Backlog
CredMgmt_10 | Story | Initiate Application | 11525761 | As a [Learner], I want to add courses and experiences (CEU) to be included in my application (continuing education) | 11523894 | ERM-2865 |  |  | This is only applicable for Renewal Applicants. DECISION 12/16: We will move forward with importing a sample extract of courses from JKO, NOVA, Coursera…etc. or other sources in order to showcase the capability. The learner will then select that course or enter in a course manually. If a learner selects a course from the pre-defined list, then the metadata will autopopulate the fields (where possible). To discuss further: applicant will need to upload proof of certification for each CEU course listed. ---- Design Notes: notes from 11/25 meeting with Andy for CEU on HOW it will be implemented: * NOTE: we want to limit options to courses that haven’t been listed yet on the application. * we are pulling/or will be pulling from 3 datasets: ** (FUTURE) xapi statements from known courses. xAPI. from ELRR completed statements. course completions that we know of that are showing up for xAPI statements. *** ECC statements. course categories are the course competencies. course category would be an extension in ECC. ** (MVP) known sapro courses (where we dontl know if completion or not) *** ECC statements. course categories are the course competencies. course category would be an extension in ECC. ** (MVP) Manually added courses – aka something brand new. ** (FUTURE) integrate ElasticSearch in search/dropdown ---- NOTE: We need to get req'd/approaved courses into ECC NOTE: requires use of simulated data until we get [Learner] record integration ---- Current Design implementation: * Dropdown has a search and filtering functionality. Users can select from bottom option to add manually instead. * Courses that aren’t eligible will be greyed out. Tooltip will provide info as to why its greyed out. Business logic for MVP: * List of approved SAPRO courses from ECC that can be counted as CEU hours * (MVP Only) no filter for if course is eligible to be included (eligibility = whether or not learner included this course in a previous application; with the exception of the ‘Ethics’ and ‘SAFE Helpline 101’, Safe Helpline 102’ course) * (MVP) hardcode SAPRO courses * (MVP) manual entry of courses if they are not in the ‘SAPRO’ approved list. * (MVP) will not include xAPI statements | Scenario: A renewal applicant is adding their CEU (continuing education) hours to their application Given: They have taken the pre-approved courses and the courses are reflected on their learner profile When: they query the ECC they can search through their learner profile AND the broader course catalog for relevant courses Then: they can select which courses are relevant that they've taken to add to their CEU section of the application Given: The applicant has taken courses not listed in the ECC / are not reflected on their learner profile When: they get to the CEU portion of the application Then: they can manually input course information and upload proof / certification |  | SAPRO | To Do
CredMgmt_11 | Story | Initiate Application | 11525762 | As a [Learner], I want to fill out information about my job shadow experience | 11523894 | ERM-2865 |  |  | NOTE: This requirement would only appear for New applicants. the system will allow the applicant to enter metadata about their 90-day job shadowing experience. These fields will include: * position name * start date * end date * hours completed * supervisor last name * supervisor first name * supervisor email ---- IN THE FUTURE, THIS COULD COME FROM ELRR: Specific [Learner] data elements on the DD form that should come from ELRR: What IS included in the ELRR: * Position Name * Employment Dates * *tries to populate supervisor name from the system it came from (if available) What is needs to be edited: * Hours * Supervisor Name * Supervisor Email Calculation of Hours: * *estimates hours based off the dates ← Deloitte to discuss if feasible/what the LOE is. ---- Data fields from HR System / ELRR: * 4.1.10.15 hasEmploymentRecord >> 4.1.8.10 Position * 4.1.10.15 hasEmploymentRecord >> 4.1.8.XX ApplicationId (Extension) * 4.1.3.4 LastName * 4.1.3.2 FirstName * Derive from 4.1.3.3 MiddleName OR 4.1.3.XX (Extension) - 4.1.3.57 HasMilitaryRecord - 4.1.10.1 militarybranch * 4.1.3.57 HasMilitaryRecord - 4.1.10.7 MilitaryCurrentStatus * 4.1.3.57 HasMilitaryRecord - 4.1.10.6 MilitaryCurrentRank * 4.1.3.57 HasMilitaryRecord - 4.1.10.31 CurrentPayGrade * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.1 OrganizationName * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.4 Facility or 4.1.7.5 Department * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.31 hasEmail * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.30 hasPhone * 4.1.3.57 HasMilitaryRecord - 4.1.10.24 isEmployedBy - 4.1.7.30 hasPhone | Feature: Select courses and experiences for advocacy application As a Learner, I want to select courses and experiences from my learner profile So that I can include relevant advocacy experience in my application. Scenario: Learner selects courses and experiences from profile Given the Learner is logged into the system And the Learner has completed courses and experiences listed in their profile When the Learner accesses the application form And selects courses and experiences to include Then the selected items should be added to the advocacy experience section of the application And the system should confirm the inclusion of selected items And the Learner should be able to review and edit the selection before submission Scenario: Learner has no courses or experiences in profile Given the Learner is logged into the system And the Learner accesses the application form When the system checks the learner profile for courses and experiences And finds no entries Then the system should display a message indicating no experiences are available And provide guidance on how to add or record relevant experiences And prevent the learner from selecting empty experience fields |  | SAPRO | Backlog
CredMgmt_12 | Story | Initiate Application | 11525763 | As a [Learner], once I submit my application it should move to the next person in the chain for review and approvals | 11523894 | ERM-2865 |  |  | New Application: * IF ‘DoD Civilian Sexual Assault Response Workforce Professional’ THEN Letter of Rec needed from a *Supervisor* * IF ‘Collateral Duty or Special Assignment SARC or SAPR VA’ THEN Statement of Understanding from their *Commander* is needed. * Job Shadowing approvals needed from supervisor (TBD). Renewal Application: ---- there is a linear chain of approvals / reviews. applicant to applicant supervisor for approval, then to 'appropriate' SARC for validation, then to NOVA admin. NOTE: The specific individuals and emails are required fields entered by the applicant. [This is correct, yes?] [~accountid:712020:53512bfe-51b0-4356-9c18-a0290c197cd3] [~accountid:609007a8f0db130069a66376] is the below correct? routing 1 → applicant to supervisor (found in required field in the application) routing 2--> supervisor to SARC (found in required field in the application) routing 3--> SARC to CO (found in required field in the application) CO to NOVA Admin (?) not sure where this will be found. | Scenario 1: Successful Submission and Routing Given: • The learner has completed all required fields in the application. • The application is in Draft/In Progress status. When: • The learner clicks Submit. Then: • The system validates the application and confirms submission with a success message. • The application status changes to Submitted. • The application is routed to the next reviewer in the approval chain. • The next reviewer receives a notification and can access the application. • An audit log entry is created with submission details. DO WE WANT TO INCLUDE A LOCKING FEATURE? where only 1 person can edit the APPLICATION at a time? Scenario 2: Post-Submission Restrictions Given: • The learner has successfully submitted the application. When: • The learner attempts to edit the application. Then: • The system prevents edits unless workflow rules explicitly allow changes. • A message informs the learner that the application is locked for review. |  | SAPRO | Internal Grooming
CredMgmt_13 | Story | Initiate Application | 11525764 | As a [Learner], I want to upload required D-SAACP certification as required for a new application | 11523894 | ERM-2865 |  |  | When the applicant is selecting “which type of application are you submitting?” and they select “New Application,” then the applicant will be prompted to upload their certificate from their completed D-SAACP pre-approved training course(s). Learner must upload the requisite Sexual Assault Prevention and Response Office (DoD SAPRO) approved training course(s). Applicants will have the ability to upload multiple course certificates to account for situations where there are one or more required training courses. ---- NOTE: We will be using Drupal for document storage. | ackground: Given the applicant is completing the application form and is selecting the type of application to submit Scenario: Prompt for Certificate Upload on New Application Given the applicant is on the application form And the applicant selects “New Application” for “Which type of application are you submitting?” When the applicant proceeds to the next step Then prompt the applicant to upload their certificate(s) from completed D-SAACP pre-approved training course(s) And display instructions that the certificate(s) must be from Sexual Assault Prevention and Response Office (DoD SAPRO) approved training courses Scenario: Allow Multiple Certificate Uploads Given the applicant is prompted to upload D-SAACP pre-approved training course certificates When the applicant has completed more than one required training course Then allow the applicant to upload multiple course certificates Scenario: Prevent Submission Without Required Certificate(s) Given the applicant has selected “New Application” When the applicant attempts to submit the application without uploading at least one D-SAACP pre-approved training course certificate Then display an error message “Upload at least one certificate from a completed D-SAACP pre-approved training course” And prevent form submission Scenario: Store Uploaded Certificates in Drupal Given the applicant uploads certificate(s) as part of the application When the upload is successful Then store the uploaded certificate(s) in Drupal for document storage |  | SAPRO | To Do
CredMgmt_14 | Story | Initiate Application | 11525765 | As a [Learner], I want to receive validation that all required data fields have been entered prior to submitting. | 11523894 | ERM-2865 |  |  | the UI should provide a red asterisks indicating required fields. If a user tries to submit and a required field is empty, the form should not be submitted and the missing field(s) should be highlighted red. Applicant will be allowed to save content during application however before the final submission, the required fields will highlight red to indicate required fields. | Scenario: The applicant believes they have completed all fields and is ready to submit their application for review Given: They have filled out all the required fields When: They reach the end of the application Then: the system will show all fields as complete in an overview and allow them to submit Given: The applicant has NOT filled out all required fields When: they reach the end of the application Then: the system will highlight incomplete fields in an overview and NOT allow them to submit until they fix the incomplete fields |  | SAPRO | To Do
CredMgmt_15 | Story | Initiate Application | 11525766 | As a [Learner], I want to see incomplete items I need to fix on my application prior to submitting it. | 11523894 | ERM-2865 |  |  | Being able to see sections greyed out in the end if they dont pass validation. | Scenario1 : The applicant has reached then end of the application but hasn't completed all items Given: They have not filled out all required fields When: They reach the final page of the application before clicking submit Then: The system will highlight incomplete items in an overview and not allow them to submit the application until they are remedied Scenario 2: The applicant has reached the end of the application and has filled out all required fields Given: They have filled out all required fields When: they reach the final page of the application to review before submitting Then: the system will mark all sections and items as complete and allow them to submit |  | SAPRO | To Do
CredMgmt_16 | Story | Initiate Application | 11525767 | As a [Learner], I want to see incorrect items I need to fix on my application prior to submitting it. | 11523894 | ERM-2865 |  |  | Like not completing all of the required fields, entering the wrong type/format of information. -user input an email that does not end in .mil or .gov !image-20251202-170307 (1b9476dc-1589-4c71-8856-fa35d1e84948).png¦width=250,alt="image-20251202-170307.png"! -user input a phone number in an invalid format / did not select/input DSN code (to be in mockup) [contains a non-numeric character / wrong amount of numbers ] | Background: Given the user is completing the application form Scenario: Validate Email Domain Given the user enters an email address When the email does not end with ".mil" or ".gov" Then display an error message "Please provide a valid .mil or .gov email address" And prevent form submission Scenario: Validate Phone Number Format and DSN selection Given the user enters a phone number When the phone number format is invalid [e.g., non-numeric character] or the DSN code is not selected Then display an error message "Phone number format invalid. Include DSN code." And prevent form submission (Might get removed) Scenario: Validate Advocacy Experience documentation when claiming > 3,900 hours Given the user answers "Yes" to "Do you have more than 3,900 hours of Sexual Assault Victim Advocacy Experience within the past two years?" When the user does not provide documentation for at least 3,900 hours Then display an error message "Upload documentation for 3,900 hours of advocacy experience" And prevent form submission (Might get removed) Scenario: Validate selection of 3 experiences for evaluation when claiming > 3,900 hours Given the user answers "Yes" to "Do you have more than 3,900 hours of Sexual Assault Victim Advocacy Experience within the past two years?" When the user does not mark at least 3 experiences for evaluation Then display an error message "Select at least 3 experiences for evaluation" And prevent form submission Scenario: Validate CEU documentation total Given the user needs to enter CEU hours When the user does not supply 32 hours of documented, new CEU Then display an error message "Provide documentation for 32 hours of CEU" And prevent form submission |  | SAPRO | To Do
CredMgmt_17 | Story | Review and Complete Application | 11525873 | As a [Org (SAPRO) Admin], I want to be able to use a check box (as a proxy for a digital signature) on required sections so that the system can track completion information. | 11523892 | ERM-2864 |  |  | SAPRO admin completes a task and needs to indicate it is complete via a checkbox Checkboxes need to be inserted on several different screens to indicate completion of different tasks by different users. Checks need to be captured / logged in the system (name, title, date, time) For *renewal* applications Specific tasks include: * Verification of sexual assault victim advocacy experience * Evaluation of sexual assault victim advocacy experience * Supervisor and Commander statement of understanding * for SARCs and SAPR-VAs Recommendation by Supervisor * Documentation of Continuing Education Training Courses For *new* applications Specific tasks include: * Verification of sexual assault victim advocacy experience * Evaluation of sexual assault victim advocacy experience * Supervisor and Commander statement of understanding * for SARCs and SAPR-VAs Recommendation by Supervisor | For all checkboxes for all SAPRO Admin roles [Supv, CO, SARC) associated with the tasks listed above .. when the check box is clicked, a popup box appears requesting confirmation of signature. When confirmation is made, data are captured in the system. and the box is filled in Scenario 1: Approve Application Using Checkbox Given The Org (SAPRO) Admin is reviewing an application for certification. Variations [new / renewal] The application meets all approval requirements. When The admin selects the digital checkbox affirming the information is accurate. Then The system records the approval action with the admin’s identity and timestamp. The application status changes to Approved. [ready to be processed by NOVA] The system removes the requirement for CAC-based digital signature. Scenario 2: Confirmation of Approval Given The admin has checked the approval box. When The system processes the approval action. Then A confirmation message appears: “Application approved successfully.” The approval is logged in the audit trail for compliance. Scenario 3: Security and Permissions Given The admin is logged in with valid credentials. When The admin attempts to approve an application using the checkbox. Then The system verifies the admin’s role and permissions before allowing the action. Unauthorized users cannot see or use the approval checkbox. |  | SAPRO | Ready for Joint Grooming
CredMgmt_18 | Story | Review and Complete Application | 11525874 | As a [Org (SAPRO) Admin], I want to provide notification and information of errors or missing information that needs to be fixed on an Applicants application. | 11523892 | ERM-2864 |  |  | applicants are currently sent canned messages. Perhaps this is email notification that they need to contact XX. | Feature: Applicant Application Error Notification As an Org (SAPRO) Admin I want to provide notification and information of errors or missing information So that applicants can correct and resubmit their applications Scenario: Admin identifies missing information in an application Given an applicant has submitted an application with missing required fields When the Admin reviews the application And the Admin marks the missing fields Then the system should generate a notification to the applicant And the notification should clearly list the missing information Scenario: Admin identifies errors in an application Given an applicant has submitted an application with incorrect data When the Admin reviews the application And the Admin flags the incorrect data Then the system should generate a notification to the applicant And the notification should clearly describe the errors Scenario: Applicant receives notification Given the Admin has flagged errors or missing information When the system sends a notification Then the applicant should receive the notification via the designated channel (e.g., email, portal message) And the notification should include instructions on how to correct the application Scenario: Applicant corrects and resubmits application Given the applicant has received a notification of errors or missing information When the applicant updates the application with the required corrections And resubmits the application Then the Admin should receive a notification And be able to review the corrected application And the system should mark the application as updated |  | SAPRO | Backlog
CredMgmt_19 | Story | Monitor Application Intake and Validation | 11525875 | As a [Org (SAPRO) Admin], I want to be notified when an applicant re-submits their application after they fixed errors in their application so I can ensure they were corrected. | 11523898 | ERM-2867 |  |  | I think(?) applicants are currently sent canned messages. Perhaps this is email notification that they need to contact XX. | Scenario: SAPRO admin had flagged errors in Applicant's application and are waiting for Applicant to fix and re-submit Given: The applicant has received the Admin's comment requiring edits, and has made the edits then re-submitted When: The applicant re-submits Then: The Admin receives an (email and in-app?) notification saying "[Applicant Name] has edited their application and re-submitted. Click to review again" or something similar that links to the section of the application they edited. |  | SAPRO | Backlog
CredMgmt_20 | Story | Monitor Application Processing | 11525876 | As a [Org (NOVA) Admin], I want to monitor application progress | 11523900 | ERM-2868 |  |  | determine & validate the steps / phases NOVA admin would want monitor … e.g., * Application intake and validation * Application packaging/preparation * Review board assignment * Approval and certification leverage existing approach to displaying progress !image-20251118-213248.png¦width=466,alt="image-20251118-213248.png"! | Feature: Monitor Application Progress As an Org (NOVA) Admin I want to monitor application progress So that I can track applicant status and ensure timely completion Scenario: Admin views application progress dashboard Given the Admin is logged into the system When the Admin navigates to the application progress dashboard Then the system should display a list of all applicants And each applicant should have a visible progress status (e.g., Not Started, In Progress, Submitted, Reviewed) Scenario: Admin views detailed progress of a single applicant Given the Admin is on the application progress dashboard When the Admin selects a specific applicant Then the system should display the applicant’s detailed progress And the details should include completed steps, pending steps, and submission date Scenario: Admin monitors overall progress statistics Given the Admin is on the application progress dashboard When the Admin requests overall progress statistics Then the system should display aggregated data (e.g., percentage of applications submitted, reviewed, pending) Scenario: Admin identifies stalled applications Given the Admin is monitoring application progress When an application has not advanced for a defined period Then the system should flag the application as stalled And the Admin should be able to view which step is pending Scenario: Admin exports progress data Given the Admin is monitoring application progress When the Admin requests an export of progress data Then the system should generate a report with applicant statuses And the report should be available in a standard format (e.g., CSV, PDF) |  | SAPRO | Backlog
CredMgmt_21 | Story | Monitor Application Intake and Validation | 11525877 | As a [Org (SAPRO) Admin], I want to monitor application progress | 11523898 | ERM-2867 |  |  | BRAINSTORMING: PROCESS = which phase the application is in… indicator or problem, stuck or failed a step in the process?? example phases / steps … * *Application Intake & Validation* * *Review & Approval Workflow* ** Multi-level review (Evaluator → Supervisor → SAPRO Admin) * *Credential Verification* ** {color:#bf2600}Check applicant eligibility against suspended/revoked lists. [do we have a requirement for this?] {color} ** Validate training completion (e.g., IVAC, ethics, Safe Helpline). * *Training & CEU Compliance* ** Confirm required 40-hour NACP training and CEU course eligibility. ** Standardize clock-hour calculations and documentation uploads. [[SAPRO Data Fields ¦ Meeting]¦https://teams.microsoft.com/l/meeting/details?eventId=AAMkADVkZTE1MWRjLWMzZWYtNDdhOC1hMWViLTk5NGEwMjJhZjgzNQBGAAAAAACaXF_IfWguQpNkSFj645JWBwAV4EYqmMrDQoyoP60KlrJMAAAAAAENAAAV4EYqmMrDQoyoP60KlrJMAARFx6uOAAA%3d] * *Digital approval & Attestation* ** Decide if a single attestation checkbox suffices or multiple signatures are needed. ** Track signature placement and approval timestamps | Feature: Monitor Application Progress As an Org (SAPRO) Admin I want to monitor application progress So that I can track applicant status and ensure timely completion Scenario: Admin views application progress dashboard Given the Admin is logged into the system When the Admin navigates to the application progress dashboard Then the system should display a list of all applicants relevant to Admin (i.e. admin is their supervisor/ writing letter of rec etc.) And each applicant should have a visible progress status (e.g., Not Started, In Progress, Submitted, Reviewed) along with the task required of the Admin and relevant dates Scenario: Admin identifies stalled applications Given the Admin is monitoring application progress When an application has not advanced for a defined period Then the system should flag the application as stalled / coming up to deadline And the Admin should be able to view which step is pending and if it's a task assigned to them as admin |  | SAPRO | Ready for Joint Grooming
CredMgmt_22 | Story | Review and Complete Application | 11525879 | As a [Org (SAPRO) Admin], I want to complete the digital letter of recommendation for applicants assigned to me. | 11523892 | ERM-2864 |  |  | Feature: Complete Digital Letter of Recommendation Provide me the appropriate recommendation template digitally with most of the information pre-populated. | Feature: Complete digital letter of recommendation for assigned applicants As an Org (SAPRO) Admin I want to complete the digital letter of recommendation for applicants assigned to me So that the recommendation is submitted and available for review in the system Scenario: Access assigned applicants Given I am logged in as an Org (SAPRO) Admin When I navigate to the "Assigned Applicants" section Then I should see a list of applicants assigned to me Scenario: Open digital letter of recommendation form Given I am viewing an applicant assigned to me When I select "Complete Letter of Recommendation" Then I should be presented with the digital recommendation form Scenario: Fill out recommendation form Given I am on the digital recommendation form When I enter all required fields (e.g., applicant details, recommendation text, rating) Then the system should validate that all mandatory fields are completed Scenario: Save draft of recommendation Given I am filling out the recommendation form When I click "Save & Exit" Then the system should store my progress without submitting the recommendation And I should be able to reopen and edit the draft later Scenario: Submit completed recommendation Given I have completed all required fields in the recommendation form When I click "Submit" (after completing any other relevant sections of app form) Then the system should mark the recommendation as completed And the applicant’s record should show the recommendation as submitted Scenario: Prevent submission of incomplete recommendation Given I have not filled out all required fields in the recommendation form When I attempt to click "Submit" Then the system should display an error message And prevent submission until all required fields are completed Scenario: Confirmation of submission Given I have submitted a completed recommendation Then I should see a confirmation message And the recommendation should be locked from further editing |  | SAPRO | Ready for Joint Grooming
CredMgmt_23 | Story | Review and Complete Application | 11525881 | As a [Org (SAPRO) Admin], I want to mark an application as reviewed and complete so that I know it is ready for submission to the next person | 11523892 | ERM-2864 |  |  | Allow me to verify the application for accuracy. Once i mark the application verified it should automatically move to the next person in the verification flow. | Feature: Mark Application as Reviewed and Complete As an Org (SAPRO) Admin I want to mark an application as reviewed and complete So that I know it is ready for submission to the next person Scenario: Admin marks application as reviewed Given the Admin has finished reviewing an applicant’s application And all required fields are complete and accurate When the Admin selects the option to mark the application as reviewed Then the system should update the application status to “Reviewed” Scenario: Admin marks application as complete Given the Admin has marked the application as reviewed When the Admin confirms the application is complete Then the system should update the application status to “Complete” And the application should be flagged as ready for submission to the next person Scenario: Prevent marking incomplete applications as complete Given the Admin is reviewing an application When the application has missing or incorrect information Then the system should prevent the Admin from marking the application as complete And the Admin should be prompted to resolve the issues (/pass back to applicant to resolve) before proceeding Scenario: Application appears in next person’s queue Given the Admin has marked the application as complete When the next person logs into the system Then the application should appear in their queue And the status should indicate “Ready for Next Review” Scenario: Audit trail of review and completion Given the Admin has marked the application as reviewed and complete When the system updates the application record Then the audit log should record the Admin’s actions And include the date, time, and Admin’s identifier |  | SAPRO | Ready for Joint Grooming
CredMgmt_24 | Story | Review and Complete Application | 11525882 | As a [Org (SAPRO) Admin], I want to be able to access and view certification applications | 11523892 | ERM-2864 |  |  | Allow me to review applications without the need to download. I want to do this all digitally. Review the application, attached documents etc.. The system should also include any relevant data from continous vetting process or any other systems that is not required by the applicant to add but still required for verificationa | Feature: Access and View Certification Applications As an Org (SAPRO) Admin I want to be able to access and view certification applications So that I can review and manage applicant submissions Scenario: Admin accesses certification applications list Given the Admin is logged into the system When the Admin navigates to the certification applications section Then the system should display a list of all certification applications And each application should show applicant name, submission date, and current status Scenario: Admin searches for a certification application Given the Admin is on the certification applications list When the Admin enters search criteria (e.g., applicant name, application ID) Then the system should filter and display matching applications And the Admin should be able to access the details of the filtered applications Scenario: Admin sorts certification applications Given the Admin is viewing the certification applications list When the Admin selects a sort option (e.g., by submission date, status) Then the system should reorder the applications accordingly And the Admin should see the updated list Scenario: Admin accesses application history Given the Admin is viewing a certification application When the Admin selects the option to view application history Then the system should display a log of actions taken on the application And the log should include dates, times, and user identifiers |  | SAPRO | Ready for Joint Grooming
CredMgmt_25 | Story | Initiate Application | 11526181 | As a [Learner], I want to download my completed application | 11523894 | ERM-2865 |  |  | After I have completed my application, and it has been filled out completely by the required individuals (e.g., SARC, Supervisor, CO, previous Supervisors…) I want to be able to access it, view my application and download it so I can share it or discuss it as/if needed. Updated Form TBD. | Scenario: Learner downloads a completed application successfully Given the learner has initiated the application and all reviewers have complete their section and the application has been sent to NOVA. And the learner is logged into the system When the learner navigates to the "My Applications" page And selects the completed application And clicks the "Download" button Then the system should generate a downloadable file of the application And the file format should be PDF And the download should start automatically And the file should contain all submitted application details Scenario: Download option is not available for incomplete applications Given the learner has an application that is not yet completed When the learner views the application details Then the "Download" button should not be visible Scenario: Error handling when download fails Given the learner has completed and submitted the application And the learner is logged into the system When the learner clicks the "Download" button And the system encounters an error generating the file Then the system should display an error message |  | SAPRO | Backlog
CredMgmt_26 | Story | Monitor Application Intake and Validation | 11526255 | As a [Learner], I want to monitor my application status all the way through submission, final approval, and certificate issuance | 11523898 | ERM-2867 |  |  | For MVP, these may be email notification rather than in-app? Applicants should receive notifications of their application’s progress, creating improved transparency throughout the process. Applicants will also be able to view their application status in the ‘applications’ page. | Feature: Learner Application Status Tracking and Notifications As a Learner I want to be notified and keep track of my application status So that I am aware of progress from submission to certificate issuance Scenario: Learner submits an application Given I have completed and submitted my application When the system receives my application Then I should see my application status as "Submitted" And I should receive a notification confirming submission Scenario: Application moves to review stage Given my application has been submitted When the application is under review Then I should see my application status as "In Review" And I should receive a notification that my application is being reviewed Scenario: Application receives final approval Given my application is under review When the application is approved Then I should see my application status as "Approved" And I should receive a notification confirming approval Scenario: Certificate is issued Given my application has been approved When the certificate is generated Then I should see my application status as "Certificate Issued" And I should receive a notification with details on accessing my certificate Scenario: Learner views application history Given I am logged into the system When I navigate to my application dashboard Then I should see a timeline of statuses including "Submitted", "In Review", "Approved", and "Certificate Issued" And each status should display the corresponding date and notification details |  | SAPRO | Backlog
CredMgmt_27 | Story | Monitor Application Intake and Validation | 11526262 | As a [Learner], I want to select the type, frequency, and method for how I am receiving notifications. | 11523898 | ERM-2867 |  |  | we should have US for this already in existing Baseline capabilities. Configure to SAPRO specific notifications. UI & email notifications? | Feature: Learner Notification Preferences As a Learner I want to select the type, frequency, and method for how I am receiving notifications So that I can control how I stay informed without being overwhelmed Scenario: Learner selects notification type Given I am logged into the system When I navigate to the notification settings Then I should be able to choose notification types such as "Application Status", "Course Updates", and "Certificate Issuance" And my selection should be saved and applied to future notifications Scenario: Learner selects notification frequency Given I am on the notification settings page When I choose a frequency option such as "Immediate", "Daily Summary", or "Weekly Digest" Then the system should deliver notifications according to my chosen frequency And I should receive a confirmation of my preference change Scenario: Learner selects notification method Given I am on the notification settings page When I choose a method such as "Email" or "In-App" Then the system should deliver notifications using my selected method And I should be able to update or change this method at any time Scenario: Learner updates preferences Given I have previously set notification preferences When I change the type, frequency, or method Then the system should immediately update my preferences And I should receive a confirmation message of the updated settings Scenario: Learner disables notifications Given I am on the notification settings page When I choose to disable a notification type Then I should no longer receive notifications of that type And the system should reflect the disabled status in my settings Scenario: Learner views current preferences Given I am logged into the system When I navigate to the notification settings Then I should see my current selections for type, frequency, and method And each preference should be clearly displayed and editable |  | SAPRO | Backlog
CredMgmt_28 | Story | Initiate Application | 11526620 | As a [Learner], I want to read a privacy act statement prior to entering in my application information. | 11523894 | ERM-2865 |  |  | Applicant will be able to read the privacy act statement and navigate back to it in the breadcrumbs if needed. Here is the updated Privacy Act Statement Language: Privacy Act Statement *AUTHORITY:* 10 U.S.C. 136, Under Secretary of Defense for Personnel and Readiness; and DoD Instruction 6495.03, Defense Sexual Assault Advocate Certification Program (D-SAACP). *PRINCIPAL PURPOSE(S):* The information on this form will be used to review and process Defense Sexual Assault Advocate Certification Program (D-SAACP) applications for all eligible Department of Defense (DoD) Sexual Assault Response Workforce (SARW) personnel. *ROUTINE USE(S):* To the Department of Justice Office for Victims of Crime and Training Technical Assistance Center for the purpose of verifying certified DoD SARW personnel for participation in Advance Military Sexual Assault Advocate Training. Additional routine uses may be found in the applicable system of records notice DHRA 10, Defense Sexual Assault Advocate Certification Program at: [https://dpcld.defense.gov/Privacy/SORNsIndex/DOD-wide-SORN-Article-View/Article/570562/dhra-10-dod/¦https://dpcld.defense.gov/Privacy/SORNsIndex/DOD-wide-SORN-Article-View/Article/570562/dhra-10-dod/¦smart-link] *DISCLOSURE:* Mandatory. If you are in an authorized DoD SARW position and you do not complete this form to receive your D-SAACP certification, you will be disqualified from the position. 10 U.S.C. 1561 | Background: Given the user is completing the application form Scenario: Display Privacy Act Statement before application entry Given the user is about to begin the application When the application form loads Then display the full Privacy Act Statement as provided in the ticket description And require the user to view the statement before entering any application information Scenario: Breadcrumb navigation to Privacy Act Statement Given the user is navigating the application form When the user views any step of the application Then display breadcrumb navigation including a link labeled "Privacy Act Statement" And allow the user to return to the Privacy Act Statement at any time Scenario: Privacy Act Statement content accuracy Given the user is viewing the Privacy Act Statement When the statement is displayed Then ensure the text matches exactly the language provided in the ticket, including bold headings and the SORN hyperlink Scenario: Accessibility of Privacy Act Statement Given the user is viewing the Privacy Act Statement When the statement is displayed Then ensure the statement is accessible (screen reader compatible, sufficient contrast, resizable text) |  | SAPRO | In Progress
CredMgmt_29 | Story | Initiate Application | 11526622 | As a [Learner], I want breadcrumbs that allow me to navigate to different sections of my application | 11523894 | ERM-2865 |  |  | I want persistent breadcrumbs when I start/re-enter my application for every section of the application so I can have visibility on where I am at, AND so I can navigate to different sections as needed. There are 4 types of breadcrumbs: *New Applications - ‘DoD Civilian Sexual Assault Response Workforce Professional’ Position* * Privacy Act > Code of Ethics > Applicant Info > Job Shadow Experience > Recommendations > Review & Send *New Applications - All other Positions* * Privacy Act > Code of Ethics > Applicant Info > Job Shadow Experience > Review & Send *Renewal Applications - ‘DoD Civilian Sexual Assault Response Workforce Professional’ Position* * Privacy Act > Code of Ethics > Applicant Info > Recommendations > CEU Documentation > Review & Send *Renewal Applications - All other Positions* * Privacy Act > Code of Ethics > Applicant Info > CEU Documentation > Review & Send | Background: The application process includes multiple sections. Users need persistent breadcrumbs to see their current location and navigate between sections. There are four breadcrumb flows, depending on application type and position. Scenario 1: New Application – ‘DoD Civilian Sexual Assault Response Workforce Professional’ Position Given the user is starting or re-entering a new application for the ‘DoD Civilian Sexual Assault Response Workforce Professional’ position When the application loads Then the breadcrumb should display: Privacy Act > Code of Ethics > Applicant Info > Job Shadow Experience > Recommendations > Review & Send And the current section should be visually highlighted And the user should be able to click any previous section in the breadcrumb to navigate to it Scenario 2: New Application – All Other Positions Given the user is starting or re-entering a new application for any position other than ‘DoD Civilian Sexual Assault Response Workforce Professional’ When the application loads Then the breadcrumb should display: Privacy Act > Code of Ethics > Applicant Info > Job Shadow Experience > Review & Send And the current section should be visually highlighted And the user should be able to click any previous section in the breadcrumb to navigate to it Scenario 3: Renewal Application – ‘DoD Civilian Sexual Assault Response Workforce Professional’ Position Given the user is starting or re-entering a renewal application for the ‘DoD Civilian Sexual Assault Response Workforce Professional’ position When the application loads Then the breadcrumb should display: Privacy Act > Code of Ethics > Applicant Info > Recommendations > CEU Documentation > Review & Send And the current section should be visually highlighted And the user should be able to click any previous section in the breadcrumb to navigate to it Scenario 4: Renewal Application – All Other Positions Given the user is starting or re-entering a renewal application for any position other than ‘DoD Civilian Sexual Assault Response Workforce Professional’ When the application loads Then the breadcrumb should display: Privacy Act > Code of Ethics > Applicant Info > CEU Documentation > Review & Send And the current section should be visually highlighted And the user should be able to click any previous section in the breadcrumb to navigate to it Scenario 5: Breadcrumb Persistence Given the user navigates between sections of the application When the user moves to a new section Then the breadcrumb should update to reflect the current section And the breadcrumb should remain visible and accurate throughout the application process Scenario 6: Navigation via Breadcrumb Given the user is on any section of the application When the user clicks a previous section in the breadcrumb Then the application should navigate to the selected section And the breadcrumb should update to highlight the new current section |  | SAPRO | To Do
CredMgmt_30 | Story | Initiate Application | 11526623 | As a [Learner], I want to read and acknowledge the code of ethics so it is clear that I understand them | 11523894 | ERM-2865 |  |  | * As a [Learner], I want to read and acknowledge the code of ethics during the application process so that it is clear I understand and agree to the ethical standards required. * The application must present the full text of the code of ethics to the learner. * The learner must be required to check a box or provide an electronic signature to acknowledge they have read and understood the code of ethics before proceeding. * This step is mandatory and must be completed before the application can be submitted. * The system should track this acknowledgment (e.g., via an xAPI statement) for auditing and compliance purposes. * This requirement is part of the MVP and should be included under the "initiate application" workflow. Here is the updated Code of Ethics Language: Every DoD Sexual Assault Response Workforce (SARW) Professional must act with integrity, treat all victims of sexual assault crimes with dignity and compassion, and uphold principles of justice for accused and accuser alike. To these ends, this Code will govern the conduct of DoD SARW Professionals: I. In relationships with every victim, the DoD SARW professionals shall: # Recognize the interests of the victim as a primary responsibility. # Respect the victim's civil and legal rights, subject only to laws requiring disclosure of information to appropriate other sources. # Respect the victim's rights to privacy and confidentiality, subject only to laws requiring disclosure. # Respond compassionately to each victim with personalized services. # Accept the victim's statement of events as it is told, withholding opinion or judgment, whether or not a suspected offender has been identified, arrested, convicted, or acquitted. # Provide services to every victim, within policy guidelines set by the DoD and the Services, without attributing blame, no matter what the victim's conduct was at the time of the victimization or at another stage of the victim’s life. # Foster maximum self-determination on the part of the victim. # Serve as a victim advocate when assigned, and in that capacity, act on behalf of the victim's stated needs and within policy guidelines set by DoD and the Services. # Should one victim's needs conflict with another's, act with regard to one victim only after promptly referring the other to another qualified DoD SARW professional. # Have no personal or sexual relations with victims currently supported by DoD SARW professionals or with alleged offenders, in recognition that to do so risks exploitation of the knowledge and trust derived from the professional relationship. # Make victim referrals to other resources or services only in the victim's best interest, avoiding any conflict of interest in the process, and do so in accordance with DoD regulations. II. In relationships with colleagues, other professionals, and the public, the DoD SARW professionals shall: # Conduct relationships with colleagues in such a way as to promote mutual respect and improvement of service. # Conduct relationships with allied professionals such that they are given equal respect and dignity as professionals in the victim assistance field. # Take steps to quell negative, insubstantial rumors about colleagues and allied professionals. # Share knowledge and encourage proficiency and excellence in victim assistance among colleagues and allied professionals, paid and volunteer. # Provide professional support, guidance, and assistance to new DoD SARW professionals to the field in order to promote consistent quality and professionalism in victim assistance. # Obey all applicable Federal, DoD, and Service laws and regulations. III. In her or his professional conduct, the SARC/SAPR VA shall: # Maintain high personal and professional standards in the capacity of a service provider and advocate for victims. # Seek and maintain a proficiency in the delivery of services to victims. # Not discriminate against any victim, employee, colleague, allied professional, or member of the public on the basis of age, sex, disability, ethnicity, race, national origin, religious belief, or sexual orientation. # In accordance with restricted reporting, applicable privileged communications, and all applicable Federal, DoD, and Service privacy laws and regulations, respect the privacy of information provided by the victims served before, during, and after the course of the professional relationship. # Clearly distinguish in public statements representing one's personal views from positions adopted by organizations for which she or he works or is a member, in accordance with Service policy. # Not use her or his official position to secure gifts, monetary rewards, or special privileges or advantages. # Notify competent authorities of the conduct of any colleague or allied professional that constitutes mistreatment of a victim or that brings the profession into disrepute. # Notify competent authorities of any conflict of interest that prevents oneself or a colleague from being able to provide competent services to a victim, or from working cooperatively with colleagues or allied professionals in a victim being impartial in the assistance of any victim. # Notify competent authority immediately if charged, arrested, and/or convicted of any criminal activity. IV. In her or his responsibility to any other profession, the DoD SARW professional will be bound by the ethical standards of the allied profession of which she or he is a member. ---- The certification language is as follows: Certification: I, the undersigned applicant, hereby certify that I have read and agree to follow the Code of Professional Ethics for DoD SARW professionals. I understand that the D-SAACP Certification is subject to surrender on demand to my SARW Program Administrator for cause, and this action may be listed in my permanent record. [ ] I acknowledge that I have read and understand the Code of Ethics for DoD SARW Professionals. | Feature: Learner acknowledges the Code of Ethics As a Learner I want to read and acknowledge the Code of Ethics So that it is clear that I understand them Scenario: Learner views the Code of Ethics Given the learner is logged into the portal When the learner hits 'continue' on the 'Privacy Act Statement Page' they are navigated to the Code of Ethics page Then the learner should see the full text of the Code of Ethics And the learner should have the option to scroll through the content And the learner should see a 'Certification' box where they can acknowledge that they have read and understand the Code of Ethics. Scenario: Learner acknowledges the Code of Ethics Given the learner has viewed the Code of Ethics When the learner clicks the "Acknowledge" checkbox Then the system should record the learner’s acknowledgement And display a confirmation that the acknowledgement was successful Scenario: Learner cannot proceed without acknowledgement Given the learner has not yet acknowledged the Code of Ethics When the learner attempts to submit / initiate application Then the system should prompt the learner to read and acknowledge the Code of Ethics first (mark as incomplete) Scenario: System stores acknowledgement Given the learner has acknowledged the Code of Ethics When an administrator reviews learner records Then the acknowledgement status should be visible within the learner’s application And the timestamp of acknowledgement should be recorded Scenario: Learner re-reads the Code of Ethics Given the learner has already acknowledged the Code of Ethics When the learner navigates back to the Code of Ethics page Then the learner should be able to view the content again And the acknowledgement status should remain recorded |  | SAPRO | In Progress
CredMgmt_31 | Story | Initiate Application | 11526658 | As a [Learner], I want to upload certifications for CEU courses I have taken | 11523894 | ERM-2865 |  |  | This requirement would only appear for Renewal applications. For each course I add to my ‘Completed Continuing Education Hours’ section, I want to upload a file of my certification that shows I completed that course. |  |  | SAPRO | Backlog